## RAID Log
ID | Type | Description | Impact | Likelihood | Owner | Mitigation / Action | Status | Evidence / Source
ID | Type | Description | Impact | Likelihood | Owner | Mitigation / Action | Status | Evidence / Source
R1 | Risk | Dataset drift between embedded workflow context and repository source files | High | Medium |  | Use a single controlled source and document version | Open | Repository workflow/data files
R2 | Risk | Synthetic replacement dataset may be mistaken for official course dataset | High | Medium |  | Label synthetic data clearly; replace with official dataset when supplied | Open | README / course materials
R3 | Risk | Baseline results or scores are not independently evidenced | High | Medium |  | Run all 12 inputs and capture outputs and scoring evidence | Open | Evaluation requirement
A1 | Assumption | Current repository uses a synthetic replacement dataset | Medium | High |  | Verify against official dataset before final submission | Open | Existing project README
I1 | Issue | Unused AI Agent node exists in exported workflow | Medium | Medium |  | Remove or document its purpose; align model configuration | Open | Mira_Workflow.json
D1 | Decision | Use router-based orchestration for specialist agents | High | High |  | Document in ADR-001 | Accepted | ADR-001-Router-Orchestration.md